Days: 1 2 3 4 5 6 7 | 8 9 |10|11 12|13 14 15|16|17 18|19|20 21|22|23 24|25|26 27|28 29 30|31 32 33 34 35

---------------------------------------------------------------------------------------------------------------

Task 1: [=======] (Gather Participants, Days 1–7)

Task 2: [==] (Organize the Event, Days 8–9)

Task 3: [ ] (Implement the Interview, Day 10)

Task 4: [==] (Record the Interview, Days 11–12)

Task 5: [===] (Analyze the Interview, Days 13–15)

Task 6: [ ] (Write Research Report, Day 16)

-------------------------------------------------------------------------------------------

Task 7: [==] (Construct Questionnaire, Days 17–18)

Task 8: [ ] (Test and Modify, Day 19)

Task 9: [==] (Do the Sampling, Days 20–21)

Task 10: [ ] (Train Interviewers, Day 22)

Task 11: [==] (Fieldwork, Days 23–24)

Task 12: [ ] (Record Data, Day 25)

Task 13: [==] (Analyze Data, Days 26–27)

Task 14: [===] (Write Final Study, Days 28–30)

-------------------------------------------------------------------------------------------

Task 15: [=====] (Buffer, Days 31–35)

**Task List with Durations and Cumulative Timeline**

**Focus Group Tasks (Total = 16 days)**

1. **Gather Participants** – 7 days  
   *Day 1 to Day 7*
2. **Organize the Event** – 2 days  
   *Day 8 to Day 9*  
   *(Starts after participants are gathered)*
3. **Implement the Interview** – 1 day  
   *Day 10*  
   *(After the event is organized)*
4. **Record the Interview** – 2 days  
   *Day 11 to Day 12*  
   *(After the interview is implemented)*
5. **Analyze the Interview** – 3 days  
   *Day 13 to Day 15*  
   *(After recording is complete)*
6. **Write Brief Research Report** – 1 day  
   *Day 16*  
   *(After analysis is finished)*

**Survey Tasks (Total = 14 days) – Begins after the Focus Group Report is complete**

1. **Construct the Questionnaire** – 2 days  
   *Day 17 to Day 18*
2. **Test and Modify the Questionnaire** – 1 day  
   *Day 19*  
   *(After construction)*
3. **Do the Sampling** – 2 days  
   *Day 20 to Day 21*
4. **Train the Interviewers** – 1 day  
   *Day 22*  
   *(After sampling)*
5. **Fieldwork** – 2 days  
   *Day 23 to Day 24*
6. **Record the Data** – 1 day  
   *Day 25*  
   *(After fieldwork)*
7. **Analyze the Data** – 2 days  
   *Day 26 to Day 27*
8. **Write the Final Study** – 3 days  
   *Day 28 to Day 30*  
   *(After analysis is complete)*

**Buffer Time**

1. **Buffer for Safety** – 5 days  
   *Day 31 to Day 35*

**Explanation**

1. **Focus Group Phase (Days 1–16):**
   * Start with gathering participants (7 days), then move on to organizing the event (2 days), implementing and recording the interview (1 + 2 days), analyzing the interview (3 days), and finally writing the report (1 day).
2. **Survey Phase (Days 17–30):**
   * Once the focus group report is complete, the survey starts with constructing the questionnaire (2 days), testing and modifying it (1 day), sampling (2 days), training interviewers (1 day), fieldwork (2 days), recording data (1 day), analyzing data (2 days), and writing the final study (3 days).
3. **Buffer (Days 31–35):**
   * An additional 5 days is allocated as a safety buffer to account for any delays or unforeseen issues